## GRAND MOSQUE
Section 1: General Information
Report Number: |  |  |  | Report Date:
Project Name: | Diriyah II Grand Mosque |  |  | Project Number: | 110
PMC: | DII-Jasara | CSC: | X-ARCHITECTS | Contractor: | MAG-MAN JV
Section 2: QMS and Submittals Status
| Total | Code A | Code B | Code C | Code D | Approved % (A & B) | Remarks/Justifications
PEP | 1 | 0 | 1 | 0 | 0 | 100%
PQP | 3 | 2 | 1 | 0 | 0 | 100%
QA/QC Procedures | 11 | 3 | 8 | 0 | 0 | 100%
MS | 71 | 13 | 46 | 9 | 3 | 83.1%
ITP | 55 | 4 | 50 | 1 | 0 | 98.18%
MAR | 171 | 1 | 120 | 43 | 7 | 70.76%
RFR | 0 | 0 | 0 | 0 | 0 | 0
SDW | 853 | 1 | 612 | 223 | 17 | 71.86%
Section 3: Non-Conformance Reports (NCRs)
| Raised NCRs | Open | Closed | Closed On-Time | Closed % | Closed On-Time % | Raised WIRs | Defect Rate % | Overdue Open NCRs | Remarks/Justifications
This month | 13 | 13 | 3 | 0 | 23.08% | 0% | 258 | 5.039%
Cumulative | 34 | 11 | 23 | 3 | 67.65% | 13.04% | 1171 | 2.904%
Section 4: Material Inspection Request (MIRs)
| Raised MIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | 20 | 12 | 12 | 60% | 100%
Cumulative | 114 | 94 | 81 | 82.46% | 86.17%
Section 5: Work Inspection Request (WIRs)
| Raised WIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | 258 | 158 | 139 | 61.24% | 87.97%
Cumulative | 1171 | 1007 | 910 | 85.99% | 90.37%
Section 6: Request For Information (RFIs)
| Total | Responded | Responded on Time | Responded % | Responded on Time % | Overdue Open RFIs | Remarks/Justifications
This month | 13 | 4 | 4 | 30.77% | 100%
Cumulative | 161 | 140 | 140 | 86.96% | 100%
Section 7: Status of Internal Audits
| Planned | Conducted | (%) Conducted | Remarks/Justifications
This Month | 0 | 0 | NA
Cumulative | 6 | 1 | 16.67%
Section 8: Audit Findings - Corrective Actions (CARs)
| Total | Open | Closed | Closed % | Remarks/Justifications
This Month | 0 |  |  | NA
Cumulative | 0 |  |  | NA
Section 9: Quality Issues and Mitigation Actions |  |  |  | Mention top 5, and mention the total number
SN. | Quality Issues | Mitigation Plan | Status (Closed / Open)
1 | Delay for test reports Submissions from contractor side | Updated logs to be presented by GC each weekly quality meeting -CSC to follow up on all required TRTs each week | Closed
2 | Quality Procedures to cover all constructions process and contractor scope of work | GCs to submit all required quality procedures with coordination with PMC and CSC quality team | Closed
3 | Weak coordination from CSC QEs with PMC quality team for all quality updates related to daily quality subjects | Instructions have been directed to CSC REs for effective coordination with JASARA quality team | Closed
4 | Effective Quality Control by CSC QEs, most of ours work at offices for QA tasks, QC part to be effectively covered | Instructions have been directed to CSC REs for effective quality control at site by CSC quality engineers | Closed
5 | Proper Quality Planning (Daily lookahead inspections log -Two weeks lookahead submissions to be in place as per PMC instructions ) | Instructions have been directed to GCs for effective quality planning(via ACONEX ) | Closed
Total | 17 | 17 | 0%
Section 10: Lessons Learned
SN. | Lessons Learned | Documented | Deployed
1 | Missing Quality Apprvolas before concrete casting | Yes | Yes
2 | Effective Coordination between Quality and Constrcution team -Contractor | Yes | Yes
3 | Missing Toolbox Talk Before the new activites at site | Yes | Yes
4 | poor Traccking for subcontractors quality delivrables by CSC &Contractor | Yes | Yes
5 | Dleay for test reports submissions from contrctor side | Yes | Yes
Total | 12 | 12 | 11
Section 11: Quality Meetings
Weekly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | 3 | 3 | 100%
Cumulative | 28 | 28 | 100%
Monthly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | 1 | 1 | 100%
Cumulative | 10 | 10 | 100%
Total | 38 | 38 | 100%
Section 12: Quality Site Walks
Weekly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | 3 | 3 | 100%
Cumulative | 18 | 18 | 100%
Monthly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | 1 | 1 | 100%
Cumulative | 9 | 9 | 100%
Total | 27 | 27 | 100%

## Waldorf Astoria Hotel & Branded
Section 1: General Information
Report Number: | 0 |  |  | Report Date:
Project Name: | Waldorf Astoria Hotel & Branded Residences |  |  | Project Number: | 108
PMC: | DII-Jasara | CSC: |  | Contractor:
Section 2: QMS and Submittals Status
| Total | Code A | Code B | Code C | Code D | Approved % (A & B) | Remarks/Justifications
PEP | 0 |  |  |  |  | 0
PQP | 0 |  |  |  |  | 0
QA/QC Procedures | 0 |  |  |  |  | 0
MS | 0 |  |  |  |  | 0
ITP | 0 |  |  |  |  | 0
MAR | 0 |  |  |  |  | 0
RFR | 0 |  |  |  |  | 0
SDW | 0 |  |  |  |  | 0
Section 3: Non-Conformance Reports (NCRs)
| Raised NCRs | Open | Closed | Closed On-Time | Closed % | Closed On-Time % | Raised WIRs | Defect Rate % | Overdue Open NCRs | Remarks/Justifications
This month |  |  |  |  | NA | NA | 0 | NA
Cumulative |  |  |  |  | NA | NA | 0 | NA
Section 4: Material Inspection Request (MIRs)
| Raised MIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month |  |  |  | NA | NA
Cumulative |  |  |  | NA | NA
Section 5: Work Inspection Request (WIRs)
| Raised WIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month |  |  |  | NA | NA
Cumulative |  |  |  | NA | NA
Section 6: Request For Information (RFIs)
| Total | Responded | Responded on Time | Responded % | Responded on Time % | Overdue Open RFIs | Remarks/Justifications
This month |  |  |  | - | -
Cumulative |  |  |  | - | -
Section 7: Status of Internal Audits
| Planned | Conducted | (%) Conducted | Remarks/Justifications
This Month |  |  | NA
Cumulative |  |  | NA
Section 8: Audit Findings - Corrective Actions (CARs)
| Total | Open | Closed | Closed % | Remarks/Justifications
This Month |  |  |  | NA
Cumulative |  |  |  | NA
Section 9: Quality Issues and Mitigation Actions |  |  |  | Mention top 5, and mention the total number
SN. | Quality Issues | Mitigation Plan | Status (Closed / Open)
Total |  |  | 0%
Section 10: Lessons Learned
SN. | Lessons Learned | Documented | Deployed
Total
Section 11: Quality Meetings
Weekly Quality Meetings | Planned | Conducted | (%) Conducted
This Month |  |  | NA
Cumulative |  |  | NA
Monthly Quality Meetings | Planned | Conducted | (%) Conducted
This Month |  |  | NA
Cumulative |  |  | NA
Total | 0 | 0 | NA
Section 12: Quality Site Walks
Weekly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month |  |  | NA
Cumulative |  |  | NA
Monthly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month |  |  | NA
Cumulative |  |  | NA
Total | 0 | 0 | NA

## OPERA HOUSE
Section 1: General Information
Report Number: | 0 |  |  | Report Date:
Project Name: | Royal Diriyah Opera House |  |  | Project Number: | 105
PMC: | DII-Jasara | CSC: | Snohetta/ Saudi Diyar | Contractor: | ECM JV
Section 2: QMS and Submittals Status
| Total | Code A | Code B | Code C | Code D | Approved % (A & B) | Remarks/Justifications
PEP | 1 | 0 | 1 | 0 | 0 | 100%
PQP | 1 | 1 | 0 | 0 | 0 | 100%
QA/QC Procedures | 11 | 0 | 11 | 0 | 0 | 100%
MS | 78 | 26 | 34 | 18 | 0 | 76.92% | The Process/ procedure's of Installation are either Incompete / Inaccurate
ITP | 47 | 16 | 20 | 10 | 1 | 76.6% | The Inspection Hold points requires update
MAR | 264 | 2 | 161 | 90 | 11 | 61.74% | The MAR's submitted by Sub-Contractors are not Reviewed
RFR | 0 | 0 | 0 | 0 | 0 | 0
SDW | 7990 | 1263 | 5275 | 1440 | 12 | 81.83% | The Shop Drawings require detailed review by ECM Teams
Section 3: Non-Conformance Reports (NCRs)
| Raised NCRs | Open | Closed | Closed On-Time | Closed % | Closed On-Time % | Raised WIRs | Defect Rate % | Overdue Open NCRs | Remarks/Justifications
This month | 10 | 10 | 1 | 0 | 10% | 0% | 701 | 1.427%
Cumulative | 41 | 20 | 21 | 18 | 51.22% | 56.25% | 6315 | 0.6492% | 11 | Delayed CAPA & Correction by ECM JV
Section 4: Material Inspection Request (MIRs)
| Raised MIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | 66 | 54 | 50 | 81.82% | 92.59%
Cumulative | 385 | 365 | 315 | 94.81% | 86.3%
Section 5: Work Inspection Request (WIRs)
| Raised WIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | 701 | 605 | 550 | 86.31% | 90.91%
Cumulative | 6315 | 6051 | 5218 | 95.82% | 86.23%
Section 6: Request For Information (RFIs)
| Total | Responded | Responded on Time | Responded % | Responded on Time % | Overdue Open RFIs | Remarks/Justifications
This month | 119 | 93 | 66 | 78.15% | 70.97%
Cumulative | 1320 | 1294 | 882 | 98.03% | 68.11% | 1
Section 7: Status of Internal Audits
| Planned | Conducted | (%) Conducted | Remarks/Justifications |  | 21+11
This Month | 1 | 1 | 100% | Pending Audit Findings
Cumulative | 1 | 1 | 100%
Section 8: Audit Findings - Corrective Actions (CARs)
| Total | Open | Closed | Closed % | Remarks/Justifications
This Month |  |  |  | NA
Cumulative |  |  |  | NA
Section 9: Quality Issues and Mitigation Actions |  |  |  | Mention top 5, and mention the total number
SN. | Quality Issues | Mitigation Plan | Status (Closed / Open)
1 | Unauthorized Welding Works and Failure to Comply with Approved Quality Requirements - Mockup (Façade) | Stop all unauthorized welding works, inspect the affected façade mockup against approved drawings and specifications, and rectify or replace any non-compliant welds/components as required. Reinspect the completed work to verify compliance, ensure only approved procedures and qualified welders are used, and strengthen QA/QC supervision and hold-point inspections to prevent recurrence. | Open
2 | Unapproved Grade 80 Steel Delivered to Site Immediate Quarantine and Strict No-Use Requirement | Immediately quarantine all delivered Grade 80 steel reinforcement, clearly label it as "Hold/Do Not Use," and prevent its incorporation into the works. Review procurement records, approved material submittals, and mill test certificates to determine the extent of the nonconformance and confirm whether the material has valid MAR and MIR approvals. Ensure that only reinforcement with approved MAR and MIR documentation is accepted and released for use. To prevent recurrence, strengthen material receiving inspections and verify reinforcement grades against approved MARs and MIRs prior to acceptance and use. | Open
3 | Issuer:During the site surveillance, it was observed that the Installed support system for cable ladder in B2-Zone 6 (hanger & support MV Cable) is not meeting the Project Requirements due to following | Load Calculation considering cables weight and threaded rods sizes,distance between supports are under Review | Open
Total | 3 | 3 | 100%
Section 10: Lessons Learned
SN. | Lessons Learned | Documented | Deployed
1 | Hanging wires supported using with plywood and channel arrangements before termination works commence to ensure safety, maintain cable integrity, and achieve a quality-compliant installation. | Yes | Yes
2 | Unauthorized concrete casting was carried out before completing the required inspection and approval process, resulting in the omission of additional reinforcement around embedded steel plates in Zone 1. This non-conformance highlights the critical importance of verifying that all reinforcement, embedded items, and related structural details are installed in accordance with approved drawings and specifications prior to concrete placement. To prevent recurrence, a strict pre-pour verification process shall be enforced, including joint inspections by Construction and QA/QC teams, use of detailed pre-pour checklists, and obtaining all required consultant approvals before casting. Proper coordination, supervision, and adherence to hold points are essential to avoid quality issues, rework, project delays, and potential structural risks. | Yes | Yes
Total | 2 | 2 | 100
Section 11: Quality Meetings
Weekly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | 4 | 4 | 100%
Cumulative | 36 | 36 | 100%
Monthly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | 1 | 1 | 100%
Cumulative | 13 | 13 | 100%
Total | 49 | 49 | 100%
Section 12: Quality Site Walks
Weekly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | 4 | 4 | 100%
Cumulative | 36 | 36 | 100%
Monthly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | 1 | 1 | 100%
Cumulative | 13 | 13 | 100%
Total | 49 | 49 | 100%

## District Level - BSW
Section 1: General Information
Report Number: | 0 |  |  | Report Date:
District Name: | Boulevard Southwest |  |  | District Abbreviation : | BSW
PMC: | DII-Jasara |  |  | Sub- Program: | BV-Boulevard Community
Section 2: QMS and Submittals Status
| Total | Code A | Code B | Code C | Code D | Approved % (A & B) | Remarks/Justifications
PEP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
PQP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
QA/QC Procedures | #REF! | #REF! | #REF! | #REF! | #REF! | 0
MS | #REF! | #REF! | #REF! | #REF! | #REF! | 0
ITP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
MAR | #REF! | #REF! | #REF! | #REF! | #REF! | 0
RFR | #REF! | #REF! | #REF! | #REF! | #REF! | 0
SDW | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Section 3: Non-Conformance Reports (NCRs)
| Raised NCRs | Open | Closed | Closed On-Time | Closed % | Closed On-Time % | Raised WIRs | Defect Rate % | Overdue Open NCRs | Remarks/Justifications
This month | #REF! | #REF! | #REF! | #REF! | NA | NA | #REF! | NA | #REF!
Cumulative | #REF! | #REF! | #REF! | #REF! | NA | NA | #REF! | NA | #REF!
Section 4: Material Inspection Request (MIRs)
| Raised MIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | #REF! | #REF! | #REF! | NA | NA
Cumulative | #REF! | #REF! | #REF! | NA | NA
Section 5: Work Inspection Request (WIRs)
| Raised WIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | #REF! | #REF! | #REF! | NA | NA
Cumulative | #REF! | #REF! | #REF! | NA | NA
Section 6: Request For Information (RFIs)
| Total | Responded | Responded on Time | Responded % | Responded on Time % | Overdue Open RFIs | Remarks/Justifications
This month | #REF! | #REF! | #REF! | - | - | #REF!
Cumulative | #REF! | #REF! | #REF! | - | - | #REF!
Section 7: Status of Internal Audits
| Planned | Conducted | (%) Conducted | Remarks/Justifications
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Section 8: Audit Findings - Corrective Actions (CARs)
| Total | Open | Closed | Closed % | Remarks/Justifications
This Month | #REF! | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | #REF! | NA
Section 9: Quality Issues and Mitigation Actions |  |  |  | Mention top 5, and mention the total number
SN. | Quality Issues | Mitigation Plan | Status (Closed / Open)
1 | Delay for test reports Submissions from contractor side | Updated logs to be presented by GC each weekly quality meeting -CSC to follow up on all required TRTs each week | Closed
2 | Quality Procedures to cover all constructions process and contractor scope of work | GCs to submit all required quality procedures with coordination with PMC and CSC quality team | Closed
3 | Weak coordination from CSC QEs with PMC quality team for all quality updates related to daily quality subjects | Instructions have been directed to CSC REs for effective coordination with JASARA quality team | Closed
4 | Effective Quality Control by CSC QEs, most of ours work at offices for QA tasks, QC part to be effectively covered | Instructions have been directed to CSC REs for effective quality control at site by CSC quality engineers | Closed
5 | Proper Quality Planning (Daily lookahead inspections log -Two weeks lookahead submissions to be in place as per PMC instructions ) | Instructions have been directed to GCs for effective quality planning(via ACONEX ) | Closed
Total | #REF! | #REF! | -
Section 10: Lessons Learned
SN. | Lessons Learned | Documented | Deployed
1 | Missing Quality Apprvolas before concrete casting | Yes | Yes
2 | Effective Coordination between Quality and Constrcution team -Contractor | Yes | Yes
3 | Missing Toolbox Talk Before the new activites at site | Yes | Yes
4 | poor Traccking for subcontractors quality delivrables by CSC &Contractor | Yes | Yes
5 | Dleay for test reports submissions from contrctor side | Yes | Yes
Total | #REF! | #REF! | #REF!
Section 11: Quality Meetings
Weekly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Monthly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Total | #REF! | #REF! | NA
Section 12: Quality Site Walks
Weekly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Monthly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Total | #REF! | #REF! | NA

## PMC Report- District level
Section 1: General Information
Report Number: | 0 |  |  | Report Date:
District Name: | Boulevard Southwest |  |  | District Abbreviation : | BSW
PMC: | DII-Jasara |  |  | Sub- Program: | BV-Boulevard Community
Section 2: QMS and Submittals Status
| Total | Code A | Code B | Code C | Code D | Approved % (A & B) | Remarks/Justifications
PEP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
PQP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
QA/QC Procedures | #REF! | #REF! | #REF! | #REF! | #REF! | 0
MS | #REF! | #REF! | #REF! | #REF! | #REF! | 0
ITP | #REF! | #REF! | #REF! | #REF! | #REF! | 0
MAR | #REF! | #REF! | #REF! | #REF! | #REF! | 0
RFR | #REF! | #REF! | #REF! | #REF! | #REF! | 0
SDW | #REF! | #REF! | #REF! | #REF! | #REF! | 0
Section 3: Non-Conformance Reports (NCRs)
| Raised NCRs | Open | Closed | Closed On-Time | Closed % | Closed On-Time % | Raised WIRs | Defect Rate % | Overdue Open NCRs | Remarks/Justifications
This month | #REF! | #REF! | #REF! | #REF! | NA | NA | #REF! | NA | #REF!
Cumulative | #REF! | #REF! | #REF! | #REF! | NA | NA | #REF! | NA | #REF!
Section 4: Material Inspection Request (MIRs)
| Raised MIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | #REF! | #REF! | #REF! | NA | NA
Cumulative | #REF! | #REF! | #REF! | NA | NA
Section 5: Work Inspection Request (WIRs)
| Raised WIRs | Approved (A & B) | Approved 1st Time | Approved % | Approved 1st Time % | Remarks/Justifications
This month | #REF! | #REF! | #REF! | NA | NA
Cumulative | #REF! | #REF! | #REF! | NA | NA
Section 6: Request For Information (RFIs)
| Total | Responded | Responded on Time | Responded % | Responded on Time % | Overdue Open RFIs | Remarks/Justifications
This month | #REF! | #REF! | #REF! | - | - | #REF!
Cumulative | #REF! | #REF! | #REF! | - | - | #REF!
Section 7: Status of Internal Audits
| Planned | Conducted | (%) Conducted | Remarks/Justifications
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Section 8: Audit Findings - Corrective Actions (CARs)
| Total | Open | Closed | Closed % | Remarks/Justifications
This Month | #REF! | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | #REF! | NA
Section 9: Quality Issues and Mitigation Actions |  |  |  | Mention top 5, and mention the total number
SN. | Quality Issues | Mitigation Plan | Status (Closed / Open)
1 | Delay for test reports Submissions from contractor side | Updated logs to be presented by GC each weekly quality meeting -CSC to follow up on all required TRTs each week | Closed
2 | Quality Procedures to cover all constructions process and contractor scope of work | GCs to submit all required quality procedures with coordination with PMC and CSC quality team | Closed
3 | Weak coordination from CSC QEs with PMC quality team for all quality updates related to daily quality subjects | Instructions have been directed to CSC REs for effective coordination with JASARA quality team | Closed
4 | Effective Quality Control by CSC QEs, most of ours work at offices for QA tasks, QC part to be effectively covered | Instructions have been directed to CSC REs for effective quality control at site by CSC quality engineers | Closed
5 | Proper Quality Planning (Daily lookahead inspections log -Two weeks lookahead submissions to be in place as per PMC instructions ) | Instructions have been directed to GCs for effective quality planning(via ACONEX ) | Closed
Total | #REF! | #REF! | -
Section 10: Lessons Learned
SN. | Lessons Learned | Documented | Deployed
1 | Missing Quality Apprvolas before concrete casting | Yes | Yes
2 | Effective Coordination between Quality and Constrcution team -Contractor | Yes | Yes
3 | Missing Toolbox Talk Before the new activites at site | Yes | Yes
4 | poor Traccking for subcontractors quality delivrables by CSC &Contractor | Yes | Yes
5 | Dleay for test reports submissions from contrctor side | Yes | Yes
Total | #REF! | #REF! | #REF!
Section 11: Quality Meetings
Weekly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Monthly Quality Meetings | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Total | #REF! | #REF! | NA
Section 12: Quality Site Walks
Weekly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Monthly Quality Site Walks | Planned | Conducted | (%) Conducted
This Month | #REF! | #REF! | NA
Cumulative | #REF! | #REF! | NA
Total | #REF! | #REF! | NA

## Metrics
SN. | P. Areas | Metrics | Description | PMC Cumulative | Target | (RAG) Criteria | Score Weight. | Target Value | Value | Remarks
1 | Leadership Enagement | M03 | The rate of conducting regular leadership Quality site walks (Monthly, Weekly). Monthly weight 40% weekly weight 60% | Weekly | Monthly: 1Weekly: 3 (excluding the monthly meeting week )100% | Green = 100% Amber = > 40% –60% Red = < 40% | 5% | 100% | NA
|  |  |  | Monthly |  |  |  |  | NA
|  | M04 | The rate of conducting regular project quality meetings (Monthly, Weekly). Monthly weight: 40%weekly weight: 60% | Weekly | Monthly: 1Weekly: 3 (excluding the monthly meeting week)100% | Green = 100% Amber = > 40% –60% Red = < 40% | 5% | 100% | NA
|  |  |  | Monthly |  |  |  |  | NA
2 | Right First-Time | M05 | The rate of First-time approval of submissions (WIR, MIR) | WIR | 85% | Green = > 85% Amber = 70 - 84% Red < 70% | 15% | 85% | NA
|  |  |  | MIR |  |  |  |  | NA
3 | Submittals Approval | M06 | The rate of approval of submittals (MS, ITP, MAR, SDW, RFR). (Code A+B) | MS | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | 0
|  |  |  | ITP |  |  |  |  | 0
|  |  |  | MAR |  |  |  |  | 0
|  |  |  | SDW |  |  |  |  | 0
|  |  |  | RFR |  |  |  |  | 0
4 | QMS Approval | M07 | The rate of QMS plans and procedures approved and revised as required (PEP, PQP, QA/QC Procedures). (Code A+B) | PEP | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | 0
|  |  |  | PQP |  |  |  |  | 0
|  |  |  | QA/QC Procedures |  |  |  |  | 0
5 | Non-Conformance | M09 | The rate of closeout of NCRs. | Closed% | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | NA
|  |  | The Rate of NCRs Closed on time% | Closed on time% | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 10% | 90% | NA
6 | Inspection Performance | M10 | The rate of Approved WIRs (Code A+B) | WIR Approved % | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | NA
|  | M11 | The rate of Approved MIRs (Code A+B). | MIR Approved % | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | NA
7 | Defect Rate | M12 | The rate of raised NCRs to conducted WIRs. | Defect Rate % | =< 2% | Green = < 2% Amber = 2.1 – 5% Red > 5% | 20% | 2% | NA
8 | Audits | M13 | The rate of audits conducted as planned and reports are issued within the designated timeframe. | (%) Conducted | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | NA
|  | M14 | The rate of timely close-out for audit findings (CARs) | Closed % | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | NA
9 | Design / Engineering | M15 | The rate of Contractor-issued RFIs responded | Responded % | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | -
|  |  | The rate of Contractor-issued RFIs responded within the agreed time frame. | Responded on Time % | 90% | Green = > 90% Amber = 70 - 89% Red < 70% | 5% | 90% | -
Overall
[6 empty] | 80%-100% | Satisfactory
[6 empty] | 60%-79% | Fair
[6 empty] | Below 60% | Poor

## Consolidated Q. Register - 01
Programme/ Project Details | [11 empty] | QA/QC Procedures & Plans Submittals | [20 empty] | Non - Conformance- NCRs | [9 empty] | Inspection Performance | [15 empty] | Request For Information (RFIs) | [7 empty] | Status of Internal Audits & Audit Findings (CARs) | [9 empty] | Quality Issues & Mitigations |  |  | Lessons Learned |  |  | Quality Meetings & Site Walks | [9 empty] | Remarks/Justifications
S.N. | Programme | Sub- Programme | District | Project Name | Project WBS unique Code | CSC | Contractor | Project lifecycle Phase | PEP |  |  | PQP |  |  | QA/QC Procedures (QMPs) |  |  | Method Statements (MS) |  |  | Inspection Test Plans ( ITPs) |  |  | Material Approval Request ( MARs) |  |  | Request For Replacement (RFR) |  |  | Shop- Drawings (SWD) |  |  | Non - Conformance- NCRs | [9 empty] | Material Inspection Requests( MIRs) | [7 empty] | Work Inspection Requests( WIRs) | [7 empty] | Request For Information (RFIs) | [7 empty] | Status of Internal Audits |  |  |  |  | Status of Audit Findings |  |  |  |  | Quality Issues & Mitigations |  |  | Lessons Learned |  |  | Quality Meetings |  |  |  |  | Quality Site Walks |  |  |  |  | Section 2: QMS and Submittals Status | [7 empty] | Section 3: Non-Conformance Reports (NCRs) |  | Section 4: Material Inspection Request (MIRs) |  | Section 5: Work Inspection Request (WIRs) |  | Section 6: Request For Information (RFIs) |  | Section 7: Status of Internal Audits |  | Section 8: Audit Findings - Corrective Actions (CARs)
[9 empty] | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | Total | Approved ( A+B) | Approved % | This Month |  |  | To Date ( Cumulative) | [6 empty] | This Month |  |  | To Date ( Cumulative) |  |  |  |  | This Month |  |  | To Date ( Cumulative) |  |  |  |  | This Month |  |  | To Date ( Cumulative) |  |  |  |  | This Month |  | To Date ( Cumulative) |  |  | This Month |  | To Date ( Cumulative) |  |  | To Date (Cumulative) |  |  | To Date (Cumulative) |  |  | This Month |  | To Date (Cumulative) |  |  | This Month |  | To Date ( Cumulative)
[33 empty] | Total | Closed | Closed On-Time | Total | Closed | Closed (%) | Closed On-time | Closed On-time (%) | Total WIRs | Defect Rate % | Total | Approved | Approved 1st Time | Total | Approved | Approval (%) | Approved 1st Time | Approved 1st Time % | Total | Approved | Approved 1st Time | Total | Approved | Approval (%) | Approved 1st Time | Approved 1st Time % | Total | Responded | Responded On-time | Total | Responded | Responded (%) | Responded On-time | Responded On-time % | Total Planned | Conducted | Total Planned | Conducted | Conducted (%) | Total | Closed | Total | Closed | Closed (%) | Total Identified Issues | Total Mitigated Issues | Mitigated (%) | Total Documented LL | Total Deployed LL | Deployed (%) | Total Planned | Conducted | Total Planned | Conducted | Conducted (%) | Total Planned | Conducted | Planned | Conducted | Conducted(%) | PEP | PQP | QA/QC Procedures | MS | ITP | MAR | RFR | SDW | This month | Cumulative | This month | Cumulative | This month | Cumulative | This month | Cumulative | This month | Cumulative | This month | Cumulative
1 | DG2 - Diriyah II | BV - Boulevard Community | BSE - Boulevard South-East | Diriyah II Grand Mosque | DD-DG2-BV-BSE-110 | X-ARCHITECTS | MAG-MAN JV | Construction | 1 | 1 | 100% | 3 | 3 | 100% | 11 | 11 | 100% | 71 | 59 | 83.1% | 55 | 54 | 98.18% | 171 | 121 | 70.76% | 0 | 0 | 0 | 853 | 613 | 71.86% | 13 | 3 | 0 | 34 | 23 | 67.65% | 3 | 13.04% | 1171 | 2.904% | 20 | 12 | 12 | 114 | 94 | 82.46% | 81 | 86.17% | 258 | 158 | 139 | 1171 | 1007 | 85.99% | 910 | 90.37% | 13 | 4 | 4 | 161 | 140 | 86.96% | 140 | 100% | 0 | 0 | 6 | 1 | 16.67% | 0 | 0 | 0 | 0 | NA | 17 | 17 | 0 | 12 | 11 | 11 | 4 | 4 | 38 | 38 | 100% | 4 | 4 | 27 | 27 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | DG2 - Diriyah II | BV - Boulevard Community | BSW - Boulevard South-West | Royal Diriyah Opera House | DD-DG2-BV-BSW-105 | Snohetta/ Saudi Diyar | ECM JV | Construction | 1 | 1 | 100% | 1 | 1 | 100% | 11 | 11 | 100% | 78 | 60 | 76.92% | 47 | 36 | 76.6% | 264 | 163 | 61.74% | 0 | 0 | 0 | 7990 | 6538 | 81.83% | 10 | 1 | 0 | 41 | 21 | 51.22% | 18 | 56.25% | 6315 | 0.6492% | 66 | 54 | 50 | 385 | 365 | 94.81% | 315 | 86.3% | 701 | 605 | 550 | 6315 | 6051 | 95.82% | 5218 | 86.23% | 119 | 93 | 66 | 1320 | 1294 | 98.03% | 882 | 68.11% | 1 | 1 | 1 | 1 | 100% | 0 | 0 | 0 | 0 | NA | 3 | 3 | 1 | 2 | 100 | 100 | 5 | 5 | 49 | 49 | 100% | 5 | 5 | 49 | 49 | 100% | 0 | 0 | 0 | The Process/ procedure's of Installation are either Incompete / Inaccurate | The Inspection Hold points requires update | The MAR's submitted by Sub-Contractors are not Reviewed | 0 | The Shop Drawings require detailed review by ECM Teams | 0 | Delayed CAPA & Correction by ECM JV | 0 | 0 | 0 | 0 | 0 | 0 | Pending Audit Findings | 0 | 0 | 0
3 | DG2 - Diriyah II | BV - Boulevard Community | BSW - Boulevard South-West | #REF! | DD-DG2-BV-BSW-106 | #REF! | #REF! | Construction | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | DG2 - Diriyah II | BV - Boulevard Community | BNW - Boulevard North-West | Waldorf Astoria Hotel & Branded Residences | DD-DG2-BV-BNW-108 | 0 | 0 | Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Consolidated Q. Register - 01 (hidden)
S.N. | Programme | Sub- Programme | District | Project Name | Project WBS unique Code | CSC | Contractor | Project lifecycle Phase | PEP, Total | PEP, Approved ( A+B) | PEP, Approved % | PQP, Total | PQP, Approved ( A+B) | PQP, Approved % | QA/QC Procedures (QMPs), Total | QA/QC Procedures (QMPs), Approved ( A+B) | QA/QC Procedures (QMPs), Approved % | Method Statements (MS), Total | Method Statements (MS), Approved ( A+B) | Method Statements (MS), Approved % | Inspection Test Plans ( ITPs), Total | Inspection Test Plans ( ITPs), Approved ( A+B) | Inspection Test Plans ( ITPs), Approved % | Material Approval Request ( MARs), Total | Material Approval Request ( MARs), Approved ( A+B) | Material Approval Request ( MARs), Approved % | Request For Replacement (RFR), Total | Request For Replacement (RFR), Approved ( A+B) | Request For Replacement (RFR), Approved % | Shop - Drawings (SWD), Total | Shop - Drawings (SWD), Approved ( A+B) | Shop - Drawings (SWD), Approved % | Non - Conformance - NCRs This Month Total | Non - Conformance- NCRs This Month Closed | Non - Conformance- NCRs This Month Closed On-Time | Non - Conformance- NCRs To Date ( Cumulative) Total | Non - Conformance- NCRs To Date ( Cumulative) Closed | Non - Conformance- NCRs To Date ( Cumulative) Closed (%) | Non - Conformance- NCRs To Date ( Cumulative) Closed On-time | Non - Conformance- NCRs To Date ( Cumulative) Closed On-time (%) | Non - Conformance- NCRs To Date ( Cumulative) Total WIRs | Non - Conformance- NCRs To Date ( Cumulative) Defect Rate % | Material Inspection Requests( MIRs) This Month Total | Material Inspection Requests( MIRs) This Month Approved | Material Inspection Requests( MIRs) This Month Approved 1st Time | Material Inspection Requests( MIRs) To Date ( Cumulative) Total | Material Inspection Requests( MIRs) To Date ( Cumulative) Approved | Material Inspection Requests( MIRs) To Date ( Cumulative) Approval (%) | Material Inspection Requests( MIRs) To Date ( Cumulative) Approved 1st Time | Material Inspection Requests( MIRs) To Date ( Cumulative) Approved 1st Time % | Work Inspection Requests( WIRs) This Month Total | Work Inspection Requests( WIRs) This Month Approved | Work Inspection Requests( WIRs) This Month Approved 1st Time | Work Inspection Requests( WIRs) To Date ( Cumulative) Total | Work Inspection Requests( WIRs) To Date ( Cumulative) Approved | Work Inspection Requests( WIRs) To Date ( Cumulative) Approval (%) | Work Inspection Requests( WIRs) To Date ( Cumulative) Approved 1st Time | Work Inspection Requests( WIRs) To Date ( Cumulative) Approved 1st Time % | Request For Information (RFIs) This Month Total | Request For Information (RFIs) This Month Responded | Request For Information (RFIs) This Month RespondedOn-time | Request For Information (RFIs) To Date ( Cumulative) Total | Request For Information (RFIs) To Date ( Cumulative) Responded | Request For Information (RFIs) To Date ( Cumulative) Responded (%) | Request For Information (RFIs) To Date ( Cumulative) RespondedOn-time | Request For Information (RFIs) To Date ( Cumulative) RespondedOn-time % | Status of Internal Audits This Month Total Planned | Status of Internal Audits This Month Conducted | Status of Internal Audits To Date ( Cumulative) TotalPlanned | Status of Internal Audits To Date ( Cumulative) Conducted | Status of Internal Audits To Date ( Cumulative) Conducted (%) | Status of Audit Findings This Month Total | Status of Audit Findings This Month Closed | Status of Audit Findings To Date ( Cumulative) Total | Status of Audit Findings To Date ( Cumulative) Closed | Status of Audit Findings To Date ( Cumulative) Closed (%) | Quality Issues & Mitigations To Date (Cumulative) Total Identified Issues | Quality Issues & Mitigations To Date (Cumulative) Total Mitigated Issues | Quality Issues & Mitigations To Date (Cumulative) Mitigated (%) | Lessons Learned To Date (Cumulative) Total Documented LL | Lessons Learned To Date (Cumulative) Total Deployed LL | Lessons Learned To Date (Cumulative) Deployed (%) | Quality Meetings This Month Total Planned | Quality Meetings This Month Conducted | Quality Meetings To Date (Cumulative) Total Planned | Quality Meetings To Date (Cumulative) Conducted | Quality Meetings To Date (Cumulative) Conducted (%) | Quality Site Walks This Month Total Planned | Quality Site Walks This Month Conducted | Quality Site Walks To Date ( Cumulative) Planned | Quality Site Walks To Date ( Cumulative) Conducted | Quality Site Walks To Date ( Cumulative) Conducted(%) | Remarks/Justifications Section 2: QMS and Submittals Status PEP | Remarks/Justifications Section 2: QMS and Submittals Status PQP | Remarks/Justifications Section 2: QMS and Submittals Status QA/QC Procedures | Remarks/Justifications Section 2: QMS and Submittals Status MS | Remarks/Justifications Section 2: QMS and Submittals Status ITP | Remarks/Justifications Section 2: QMS and Submittals Status MAR | Remarks/Justifications Section 2: QMS and Submittals Status RFR | Remarks/Justifications Section 2: QMS and Submittals Status SDW | Remarks/Justifications Section 3: Non-Conformance Reports (NCRs) This month | Remarks/Justifications Section 3: Non-Conformance Reports (NCRs) Cumulative | Remarks/Justifications Section 4: Material Inspection Request (MIRs) This month | Remarks/Justifications Section 4: Material Inspection Request (MIRs) Cumulative | Remarks/Justifications Section 5: Work Inspection Request (WIRs) This month | Remarks/Justifications Section 5: Work Inspection Request (WIRs) Cumulative | Remarks/Justifications Section 6: Request For Information (RFIs) This month | Remarks/Justifications Section 6: Request For Information (RFIs) Cumulative | Remarks/Justifications Section 7: Status of Internal Audits This month | Remarks/Justifications Section 7: Status of Internal Audits Cumulative | Remarks/Justifications Section 8: Audit Findings - Corrective Actions (CARs) This month | Remarks/Justifications Section 8: Audit Findings - Corrective Actions (CARs) Cumulative
1 | DG2 - Diriyah II | BV - Boulevard Community | BSE - Boulevard South-East | Diriyah II Grand Mosque | DD-DG2-BV-BSE-110 | X-ARCHITECTS | MAG-MAN JV | Construction | 1 | 1 | 1 | 3 | 3 | 1 | 11 | 11 | 1 | 71 | 59 | 0.83099 | 55 | 54 | 0.98182 | 171 | 121 | 0.7076 | 0 | 0 | 0 | 853 | 613 | 0.71864 | 13 | 3 | 0 | 34 | 23 | 0.67647 | 3 | 0.13043 | 1171 | 0.029035 | 20 | 12 | 12 | 114 | 94 | 0.82456 | 81 | 0.8617 | 258 | 158 | 139 | 1171 | 1007 | 0.85995 | 910 | 0.90367 | 13 | 4 | 4 | 161 | 140 | 0.86957 | 140 | 1 | 0 | 0 | 6 | 1 | 0.16667 | 0 | 0 | 0 | 0 | NA | 17 | 17 | 0 | 12 | 11 | 11 | 4 | 4 | 38 | 38 | 1 | 4 | 4 | 27 | 27 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | DG2 - Diriyah II | BV - Boulevard Community | BSW - Boulevard South-West | Royal Diriyah Opera House | DD-DG2-BV-BSW-105 | Snohetta/ Saudi Diyar | ECM JV | Construction | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 11 | 1 | 78 | 60 | 0.76923 | 47 | 36 | 0.76596 | 264 | 163 | 0.61742 | 0 | 0 | 0 | 7990 | 6538 | 0.81827 | 10 | 1 | 0 | 41 | 21 | 0.5122 | 18 | 0.5625 | 6315 | 0.0064925 | 66 | 54 | 50 | 385 | 365 | 0.94805 | 315 | 0.86301 | 701 | 605 | 550 | 6315 | 6051 | 0.95819 | 5218 | 0.86234 | 119 | 93 | 66 | 1320 | 1294 | 0.9803 | 882 | 0.68108 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | NA | 3 | 3 | 1 | 2 | 100 | 100 | 5 | 5 | 49 | 49 | 1 | 5 | 5 | 49 | 49 | 1 | 0 | 0 | 0 | The Process/ procedure's of Installation are either Incompete / Inaccurate | The Inspection Hold points requires update | The MAR's submitted by Sub-Contractors are not Reviewed | 0 | The Shop Drawings require detailed review by ECM Teams | 0 | Delayed CAPA & Correction by ECM JV | 0 | 0 | 0 | 0 | 0 | 0 | Pending Audit Findings | 0 | 0 | 0
3 | DG2 - Diriyah II | BV - Boulevard Community | BSW - Boulevard South-West | #REF! | DD-DG2-BV-BSW-106 | #REF! | #REF! | Construction | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | DG2 - Diriyah II | BV - Boulevard Community | BNW - Boulevard North-West | Waldorf Astoria Hotel & Branded Residences | DD-DG2-BV-BNW-108 | 0 | 0 | Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | - | 0 | - | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Consolidated Q. Register - 02
Consolidated Quality Monitoring Register - 02
Section 9 ( Quality Issues and lessons Learned)
S.N. | Programme | Sub- Programme | District | Project Name | Project WBS unique Code | Project lifecycle Phase | Section 9: Quality Issues and Mitigation Actions
[7 empty] | Quality Issues | Mitigation Plan | Status (Open/ Closed)

## Consolidated Q. Register - 03
Consolidated Quality Monitoring Register - 03
Section 10 ( Quality Issues and lessons Learned)
S.N. | Programme | Sub- Programme | District | Project Name | Project WBS unique Code | Project lifecycle Phase | Section 10: Lessons Learned
[7 empty] | Lessons Learned | Documented | Deployed