## L.L CSC Register Diyar
DD-2023-329 - Diriyah II Management Contracting – Opera House Learning Event Register- CSC
Project Name | Diriyah II Management Contracting – Opera House | [6 empty] | Legend
[8 empty] | Open | P | Learning Event | LE
Project WBS | DD-2023-329 | [6 empty] | In Progress | IP | Best Practice | BP
[8 empty] | Closed | C | Lesson learned | LL
Learning Event ID | Learning Event (LE) Title | LE Type (LL / BP) | Classification (Technical / Process) | Description | Date | Project Phase | Function | Impact | Recommendation / Action Taken | Status (P / IP / C) | Responsible Person
1 | Premature Removal of Slab Formwork at Pour Strip Location | LL | Technical / Technology | Removal of Slab Formwork at Pour Strip Location (Zone 3 – B1) | 18-02-2026 | Execution | Construction | Quality | Moving forward, it shall be ensured that the form works at cantilevered portion of slab shall be left untouched at the pour strip locations. Required training to the team in this regard shall be provided. | Closed | Construction Manager
2 | Exposed concrete requires strict control over formwork quality, proper sealing of joints, accurate alignment, controlled concrete placement, and continuous supervision | LL | Management System / Process | The contractor has not achieved the required quality of finishing for exposed concrete works. Several defects were observed, including uneven surface finish, segregation, cold joints, and improper alignment, indicating inadequate formwork preparation, poor concrete placement practices | 28-02-2026 | Execution | Construction | Quality | The contractor shall improve formwork system and ensure proper alignment, rigidity, and joint sealing before casting. Skilled manpower and close supervision must be assigned during concrete placement and vibration. | Closed | Construction Director
3 | MEP openings were not properly secured and checked prior to concrete casting | LL | Management System / Process | Multiple MEP openings were found misaligned and deflected after removal of the formwork | 2026-04-03 | Execution | Construction | Quality | Ensure proper fixing and bracing of MEP openings before concrete pouring. Conduct joint inspection with MEP, QA/QC, and survey teams before casting Maintain continuous monitoring during concreting | Closed | Construction Manager
4 | Low KPI Performance in Prequalification & Material Submittals | LL | Technical / Technology | KPI below target due to poor coordination and incomplete/unchecked submittals leading to Code C. | 15/3/2026 | Documention | Procurement | Time | Implement mandatory internal QA/QC review before submission.Conduct coordination meetings between procurement & QA/QC | In progress | Procurement Manager
5 | Wall Casting Without Mechanical Inspection – Zone C (B2-01) | LL | Management System / Process | Wall casting was carried out without approved inspection. Formwork was closed before inspection | 2026-12-04 | Execution | Quality | Quality | Ensure WIR submission before formwork closure, do not proceed without inspection approval, and improve coordination between civil and mechanical teams. | Closed | Construction Manager
6 | Improper Sequence of EMT Conduit Installation in B1 Zone 2 & 3 | LL | Management System / Process | EMT conduits were installed before completion of ceiling painting, not following the approved sequence. | 20/4/2026 | Execution | Construction | Time | Follow approved method statement and proper work sequence; start EMT installation only after completion of painting and related works. | Closed | MEP Manager
7 | Insufficient QC Personnel Deployment Leading to Non-Compliance | LL | Management System / Process | During site execution, it was observed that the number of assigned QC personnel was not adequate to cover ongoing activities and site surveillance requirements. This resulted in insufficient quality monitoring and delayed identification of non-conformances. | 2026-05-03 | Execution | Quality | Quality | Ensure proper allocation and continuous presence of qualified QC personnel at site in line with project activities. Improve manpower planning, shift coverage, and monitoring system to strengthen quality control and prevent recurrence of non-compliances. | In progress
8 | MEP Installation without Architectural Clearance for Exposed Slab Finishing | LL | Management System / Process | MEP installation works were carried out on exposed concrete slab areas without obtaining prior architectural clearance for surface finishing approval. This resulted in non-compliance with approved project procedures and coordination requirements between disciplines. | 2026-05-21 | Execution | Construction | Time | Ensure strict enforcement of architectural clearance approval prior to commencement of any MEP installation on exposed or finished concrete surfaces | Open
9 | No inspection/ visit of the Concrete Batch Plant has been conducted since September 2025 | LL | Management System / Process | It was observed that the Contractor's Quality Team has not conducted any visits to the Uni-Beton batch plant since the approval of the trial mix in September 2025 to verify the plant's quality control processes and production activities | 2026-06-15 | Execution | Quality | Quality | The Contractor and the CSC conducted a joint surveillance visit to the Uni-Beton batch plant. All equipment and measuring devices, including the batching plant, were found to be properly calibrated. Raw materials were adequately segregated and stored in accordance with standard practices | Closed | ECM QA/QC Manager
10 | Competency of Third Party Inspectors | LL | Technical / Technology | During the site NDT inspection, it was noted that the Third-Party Inspector performing the Non-Destructive Testing was not ASNT Level II certified as required by the project specifications. | 2026-06-22 | Execution | Quality | Quality | An ASNT Level II certified Third-Party Inspector was assigned to perform the inspection activities, and the required tests were conducted in accordance with the approved inspection and test requirements. | Closed | ECM QA/QC Manager

## L.L Contrctor ECM
DD-2023-329 - Diriyah II Management Contracting – Opera Block Lessons Learned Register - Contrctor (ECM )
Project Name | Diriyah II Management Contracting – Opera House | [6 empty] | Legend
[8 empty] | Open | P | Learning Event | LE
Project WBS | DD-2023-329 | [6 empty] | In Progress | IP | Best Practice | BP
[8 empty] | Closed | C | Lesson learned | LL
Learning Event ID | Learning Event (LE) Title | LE Type (LL / BP) | Classification (Technical / Process) | Description | Date | Project Phase | Function | Impact | Recommendation / Action Taken | Status (P / IP / C) | Responsible Person
BV-BSW-105-0000-ECM-RPT-LL-000001 | Formwork Uplift Due to Excessive Height of Blinding Concrete in Single Pour | LL | Management System / Process | Blinding Concrete pouring was carried out in a single stage up to approximately 1m height. This resulted in uplift and displacement of the Formwork during concreting. | 27-08-2025 | Execution | Construction | Cost | Sufficient supports shall be provided to all formworks if the height of the blinding is more. Also, necessary care shall be taken during the concreting. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000002 | Poor Bonding of SikaProof A+12 Waterproofing Due to Early Disturbance of Formwork | LL | Management System / Process | Poor Bonding of Sika Proof A+12 Waterproofing System applied to the formwork | 2025-04-12 | Execution | Construction | Quality | The form work to which the FPO is attached shall not be disturbed till the heat of hydration is subsided. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000003 | Incorrect Installation of Rebar Couplers Due to Non-Compliance with Manufacturer’s Procedure | LL | Management System / Process | The rebar couplers were installed incorrectly and did not comply with the manufacturer’s approved installation procedure. | 15-01-2026 | Execution | Construction | Quality | Training from manufacturer was conducted and following protocol set: - One rebar must be full-threaded, and the mating rebar half-threaded. - The coupler must first be fully installed onto the full-threaded rebar. - The coupler should then be aligned with the half-threaded rebar, ensuring the chamfered side of the coupler faces the half-threaded rebar. - The coupler must be rotated as necessary to ensure the half-threaded portion is fully engaged and covered. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000007 | Early de-shuttering observed for Structural Wall P10-24 at Zone 10 - B2 Inner Wall | LL | Management System / Process | Early de-shuttering for Structural Wall will may cause a deflection due to incomplete concrete compressive strength reach out | 2026-05-03 | Execution | Construction | Quality | De-shuttering will be carried out only after approved WIR and submission of 3/7 days third-party test reports confirming at least 70% concrete strength. Compliance will be ensured prior to removal of supports. | Open | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000008 | Containment work started without NTS (Notice To Start) approval | LL | Management System / Process | Work was initiated before obtaining the required NTS approval, indicating a gap in coordination and adherence to the approval process. | 2026-12-04 | Execution | Construction | Quality | A Quality Toolbox Talk (TBT) was conducted to improve site coordination and highlight the importance of securing all required approvals before starting work. Compliance with procedures will be reinforced | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000009 | (First course grouted before Survey WIR approval at Zone D, B1 | LL | Management System / Process | CMU (Masonry) activity was carried out without following the planned sequence as per the approved Inspection & Test Plan (ITP). | 15-05-2026 | Execution | Construction | Quality | CMU construction team will be followed the approved ITP and Method Statement for proper sequence of work. A Toolbox Talk (TBT) will be conducted to improve awareness and ensure adherence. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000010 | Improper Installation of Embedded Plates for Façade Support System at Zone 8, Ground Floor | LL | Management System / Process | Installation procedure of Embedded plates not follwed as per standards and project requirements. | 15-06-2027 | Execution | Construction | Quality | Embedded Plates for Façade Support System to follow correct sequence of work with approved MSRA, ITP, MIR & WIR. TBT conducted to Facade construction team. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000011 | Lack of signage and TBT awareness for critical SF#3 walls in Basement B2. | LL | Management System / Process | The SF#3 walls in the Basement B2 were not protected by signage and/or any TBT was not conducted to the Labors / Technicians / Foreman as awareness of Critical walls/ columns | 20-07-2026 | Execution | Construction | Quality | Warning signage stating "Graffiti Not Allowed" was installed on the walls, and a Toolbox Talk (TBT) was conducted to raise awareness among the site team regarding wall protection requirements and prevention of graffiti. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000012 | Protection of Exposed Electrical Small power Conductors | LL | Management System / Process | Pulled small power cables/conductors were not adequately protected against damage from ongoing construction activities. | 23-07-2026 | Execution | Construction | Quality | Exposed wires were properly secured, provided with mechanical protection, and labeled for easy identification. The area was inspected and found compliant with safety and project requirements and also Conducted TBT. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000013 | Deficient Installation of EMT Conduits and Junction Boxes at Beam Crossings | LL | Management System / Process | EMT conduits and junction boxes at beam crossing locations were installed improperly and not in accordance with approved drawings and standard installation requirements. | 24-07-2026 | Execution | Construction | Quality | Mock WIR submitted for EMT conduits with proper bending and quality installation practices. This ensures compliance with project standards, improves workmanship quality, and avoids rework during inspection and execution stages. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000014 | Improved Material Storage of Pipe at site | LL | Management System / Process | MEP pipes were initially stored directly on the floor, creating housekeeping concerns, potential trip hazards, and risk of material damage. | 26-07-2026 | Execution | Construction | Quality | Provided dedicated storage racks for pipes, conduits, and similar materials at work areas and storage zones. Materials shall be stacked systematically and segregated by size. Ensure housekeeping inspections are conducted regularly to prevent floor obstructions and reduce manual handling risks. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000015 | Hanging wires were left unsupported | LL | Management System / Process | LV Wires were observed hanging without adequate support.Wires were not properly secured to a dedicated support,which could lead to cable strain, damage to insulation, stress on terminations. | 27-08-2026 | Execution | Construction | Quality | Hanging wires supported using with plywood and channel arrangements before termination works commence to ensure safety, maintain cable integrity, and achieve a quality-compliant installation. | Closed | Construction Manager
BV-BSW-105-0000-ECM-RPT-LL-000016 | Unauthorized concrete casting was carried out before completing the required inspection | LL | Management System / Process | Unauthorized concrete casting was carried out before completing the required inspection and approval process, resulting in the omission of additional reinforcement around embedded steel plates in Zone 1 | 27-08-2026 | Execution | Construction | Quality | .This non-conformance highlights the critical importance of verifying that all reinforcement, embedded items, and related structural details are installed in accordance with approved drawings and specifications prior to concrete placement. To prevent recurrence, a strict pre-pour verification process shall be enforced, including joint inspections by Construction and QA/QC teams, use of detailed pre-pour checklists, and obtaining all required consultant approvals before casting. Proper coordination, supervision, and adherence to hold points are essential to avoid quality issues, rework, project delays, and potential structural risks. | Closed | Construction Manager
27
28

## Dropdown Lists
Status | Deployment Type | LE Type | LE Classification | Functions | Impact | Knowledge Area | Project Phase
Open | Company Newsletter | LL | Technical / Technology | Project Integration | Cost | Integration | Initiation
Closed | Process Update | BP | Management System / Process | Design | Time | Scope and Change | Planning
In-Progress | Training |  |  | Construction | Quality | Schedule | Execution
| Others |  |  | Procurement | HSE | Cost & Contract | Monitoring & Controlling
|  |  |  | Contract Administration | Sustainability | Quality | Closure
|  |  |  | Budget and Cost | Stakeholders | Resource
|  |  |  | Change Control |  | Communications
|  |  |  | Claims Administration |  | Risk
|  |  |  | Project Controls & Reporting |  | Procurement
|  |  |  | Documentation & Communication |  | Stakeholder Management
|  |  |  | Planning / Scheduling |  | HSE
|  |  |  | Quality |  | Sustainability
HSE
Risk
Stakeholders & Interface
Completion (T&C, HO, and Closeout)